## Municipal Buildings
| City of Methuen: Priority for ADA Transition Plan - Municipal Buildings | [9 empty] | IHCD Cost Estimation Notes: - Cost of design is not included. - Does not include costs when note indicates future work. - Labor cannot be estimated for all remedies. - There is no cost noted when it's presumed to be a maintenance issue. - Cost based on a national average. Cost is not based on prevailing wage. - There is no cost noted when it's presumed to be a maintenance issue. -Does not include costs for accessibility renovation to outdoor areas. Estimates are intended as a guide to budgeting access modifications and are not intended to be absolutely comprehensive or definitive.
| Priorities: Priority 1: Program Access* or Safety Priority 2: Navigational Issue Priority 3: Additional Access* Priority 4: Enhanced Usability | [5 empty] | *Note: Some toilet rooms issues compromise Program Access. Some toilet rooms with less central issues (e.g., partially accessible toilet rooms), fall under Additional Access.
| Information Provided by Institute for Human Centered Design | [10 empty] | Project Management for the City of Methuen
ID | Facility Name | Element | Issue/Physical Barrier | Location | Fl. | Rm. | Town Priority | Priority for Barrier Removal | Remedies | Quantity | Estimated Cost of Barrier Removal | Project Start Date | Project Completion Date | Responsible for Barrier Removal
1 | Methuen Fire Department | C. Off-Street Parking Lot or Garage | A. Total # of parking E. Van space < 132" or <96" wide G. Access aisle not provided K. Access aisle < 96" wide at van space N. Sign with the International Symbol of Acc. not provided O. Sign does not have the designation "Van Accessible" | Parking Lot | Ext. |  | Priority 1 | Program Access | Provide a van accessible space that is at least 96" wide with a marked access aisle that is at least 96" wide. Provide a sign with the International Symbol of Accessibility (ISA) with the bottom of the sign 60" min. above the ground and the top 96" max. above the ground. Add the designation "Van Accessible" to the sign located at the van accessible space. (Cost estimate is for the sign.) | 1 | 500
2 | Methuen Fire Department | K. Entrance | E. Clear width at door is < 32" G. Maneuvering clearance is not provided O. Vertical clearance < 80" above ground | Main Entrance | Ext. |  | Priority 1 | Program Access | Install offset hinges to ensure that the door has a clear width of 32 inches. The support for the roof obstructs the maneuvering clearance at the door and acts as a protruding object in the circulation path. (Cost estimate is for cane-detectable barriers on each side of door (consider providing fixed planters), an automatic door opener and providing a door with offset hinges.) | 1 | 9698
3 | Methuen Fire Department | A. Means of Egress | B. Tactile exit sign not provided | Main Entrance | 1 |  | Priority 1 | Program Access | Ensure that a tactile exit sign with raised characters and braille is provided at the exit door. Mount the sign between 48”- 60” above the finished floor located on the latch side of the door. If and when an illuminated sign is provided at the exit door, it should contain an International Symbol of Accessibility (ISA). | 1 | 250
4 | Methuen Fire Department | K. Signage | A. Signage is not provided | Single-User Toilet Room (Bay) | 1 |  | Priority 1 | Program Access | Locate compliant signage with raised characters and braille alongside the door on the latch side. | 1 | 250
5 | Methuen Fire Department | A. Overall Access | C. Accessible plumbing fixtures or stalls not provided K. Audible and visible alarm not provided X. Clear width at door < 32" Y. Threshold not beveled Z. Hardware not compliant | Single-User Toilet Room (Bay) | 1 |  | Priority 1 | Program Access | Provide an accessible single-user toilet room. Widen the door so that there is 32" min. clear width. Bevel the threshold. Provide hardware that can be operable with one hand and not require tight grasping, pinching, or twisting of the wrist. When fire system is updated, ensure that a visible and audible fire alarm is installed. (Cost estimate is typical for an accessible toilet room.) | 1 | 31985
1 | Methuen Senior Activity Center | A. Exterior Access Route | E. Obstructed by protruding objects | Exterior Route on South/East Side of Building (Front Entrance Door) | Ext. | - | Priority 3 | Additional Access | Provide a cane-detectable barrier under the light or provide a light fixture with a narrower profile. (Cost estimate is for a cane-detectable barrier.) | 1 | 398
2 | Methuen Senior Activity Center | A. Exterior Access Route | F. Surface openings > 1/2" M. Route not maintained in operable working condition | Path From Rt. 113 Sidewalk to Front Entrance (South/East Door) | Ext. | - | Priority 1 | Program Access | Ensure that the surface opening is no greater than 1/2" max. Ensure the accessible route is maintained in operable working condition. | 1 | 0
3 | Methuen Senior Activity Center | A. Exterior Access Route | G. Cross slope > 1:50 (2.00%) | Sidewalk on Barker Street (North/East Border of Site) | Ext. | - | Priority 3 | Additional Access | Reduce cross slope to be no steeper than 1:50 (2.00%). | 1 | 0
4 | Methuen Senior Activity Center | A. Exterior Access Route | G. Cross slope > 1:50 (2.00%) | Sidewalk on Barker Street (North/East Border of Site) | Ext. | - | Priority 3 | Additional Access | Reduce cross slope to be no steeper than 1:50 (2.00%). | 1 | 0
5 | Methuen Senior Activity Center | A. Exterior Access Route | G. Cross slope > 1:50 (2.00%) | Sidewalk on Rt. 113 (South/East Border of Site) | Ext. | - | Priority 3 | Additional Access | Reduce cross slope to be no steeper than 1:50 (2.00%). | 1 | 0
6 | Methuen Senior Activity Center | A. Exterior Access Route | G. Cross slope > 1:50 (2.00%) | Sidewalk on Rt. 113 (South/East Border of Site) | Ext. | - | Priority 3 | Additional Access | Reduce cross slope to be no steeper than 1:50 (2.00%). | 1 | 0
7 | Methuen Senior Activity Center | A. Exterior Access Route | G. Cross slope > 1:50 (2.00%) | School Street Sidewalk (South/West Border of Site) | Ext. | - | Priority 3 | Additional Access | Reduce cross slope to be no steeper than 1:50 (2.00%). | 1 | 0
8 | Methuen Senior Activity Center | A. Exterior Access Route | G. Cross slope > 1:50 (2.00%) | School Street Sidewalk (South/West Border of Site) | Ext. | - | Priority 3 | Additional Access | Reduce cross slope to be no steeper than 1:50 (2.00%). | 1 | 0
9 | Methuen Senior Activity Center | A. Exterior Access Route | G. Cross slope > 1:50 (2.00%) | School Street Sidewalk (South/West Border of Site) | Ext. | - | Priority 3 | Additional Access | Reduce cross slope to be no steeper than 1:50 (2.00%). | 1 | 0
10 | Methuen Senior Activity Center | A. Exterior Access Route | J. Level changes > 1/4" | Path From Rt. 113 Sidewalk to Front Entrance (South/East Door) | Ext. | - | Priority 3 | Additional Access | Alter change in level to be 1/4" high max. | 1 | 0
11 | Methuen Senior Activity Center | A. Exterior Access Route | M. Route not maintained in operable working condition | Sidewalk on Corner of Barker Street and Rt. 113 | Ext. | - | Priority 1 | Program Access | Ensure the accessible route is maintained in operable working condition. | 1 | 0
12 | Methuen Senior Activity Center | A. Exterior Access Route | F. Surface openings > 1/2" M. Route not maintained in operable working condition | School Street Sidewalk (South/West Border of Site) | Ext. | - | Priority 1 | Program Access | Ensure that the surface opening is no greater than 1/2" max. Ensure the accessible route is maintained in operable working condition. | 1 | 0
13 | Methuen Senior Activity Center | B. Curb Ramp | E. Curb ramp flares > 1:10 (10%) | Sidewalk on Corner of Barker Street and Rt. 113 | Ext. | - | Priority 1 | Program Access | Reduce slope at curb ramp flares to be no steeper than 1:10 (10%). Applies to both flares. | 2 | 0
14 | Methuen Senior Activity Center | C. Off-Street Parking Lot or Garage | P. Sign bottom < 60" above finished grade | Accessible Parking by Back Entrance | Ext. | - | Priority 1 | Program Access | Locate sign with the bottom of the sign 60" above the ground. | 1 | 0
15 | Methuen Senior Activity Center | C. Off-Street Parking Lot or Garage | P. Sign bottom < 60" above finished grade | Accessible Parking by Back Entrance | Ext. | - | Priority 1 | Program Access | Locate sign with the bottom of the sign 60" above the ground. | 1 | 0
16 | Methuen Senior Activity Center | F. Exterior Stair | D. Handrails do not extend 12" from stair at top E. Bottom handrail extends < 12" + one tread F. Cross section of handrail is not compliant | Stair by School Street | Ext. | - | Priority 1 | Safety | Replace the rails; ensure new rails provide handrails that extend horizontally above the landing for 12” min. beginning above the first riser nosing, have sloped bottom handrail extensions that extend one tread depth min. beyond last riser nosing in same direction as stair flight, and provide handrails with 1 1/4" - 2" circular cross sections. | 1 | 0
17 | Methuen Senior Activity Center | F. Exterior Stair | E. Bottom handrail extends < 12" + one tread F. Cross section of handrail is not compliant | Egress Door Leading to Barker Street Sidewalk (East) | Ext. | - | Priority 1 | Safety | Replace the rails; ensure new rails have sloped bottom extensions that extend one tread depth min. beyond last riser nosing in same direction as stair flight, and provide handrails with 1 1/4" - 2" circular cross sections. | 1 | 0
18 | Methuen Senior Activity Center | F. Exterior Stair | C. Handrail height < 34" or > 38" E. Bottom handrail extends < 12" + one tread F. Cross section of handrail is not compliant H. Handrail not provided on both sides | Entrance Door to Thrift Shop | Ext. | - | Priority 1 | Safety | Alter so the handrails are 34"- 38" high above the finished floor or ground. Bottom: Ensure that the sloped bottom extension extends one tread depth min. beyond last riser nosing in same direction as stair flight. Provide handrails with 1 1/4" - 2" circular cross sections. Provide a handrail on each side. | 1 | 0
19 | Methuen Senior Activity Center | F. Exterior Stair | D. Handrails do not extend 12" from stair at top E. Bottom handrail extends < 12" + one tread F. Cross section of handrail is not compliant H. Handrail not provided on both sides O. Surface not stable, firm, and slip-resistant Z. Handrail not maintained in operable working condition | North Emergency Egress Stair | B | - | Priority 1 | Safety | Ensure handrails extend horizontally above the landing for 12” min. beginning above the first riser nosing. Ensure that the sloped bottom extension extends one tread depth min. beyond last riser nosing in same direction as stair flight. Provide handrails with 1 1/4" - 2" circular cross sections. Provide a handrail on each side. Ensure that the surface is cleared of debris. Ensure the handrail is maintained. | 1 | 0
20 | Methuen Senior Activity Center | F. Exterior Stair | P. Not maintained in operable working condition | Entrance Door to Thrift Shop | Ext. | - | Priority 1 | Program Access | Ensure stairs are maintained in operable working condition. The cross slope at the landing is 2.6%. | 1 | 0
21 | Methuen Senior Activity Center | K. Entrance | C. Directional sign to accessible entrance not provided | Entrance Door to Thrift Shop | Ext. | - | Priority 1 | Program Access | Provide a directional sign indicating the location of the nearest accessible entrance. | 1 | 450
22 | Methuen Senior Activity Center | K. Entrance | C. Directional sign to accessible entrance not provided | Egress Door Leading to Barker Street Sidewalk (East) | Ext. | - | Priority 1 | Program Access | Provide a directional sign indicating the location of the nearest accessible entrance at the bottom corner of the staircase. Applies to both sliding doors at the auditorium. | 3 | 1350
23 | Methuen Senior Activity Center | K. Entrance | D. International Symbol of Accessibility not provided | Back Entrance (North Side of Building) Applies to South/East Front Entrance Facing Rt. 113 | Ext. | - | Priority 1 | Program Access | Provide a sign with the International Symbol of Accessibility (ISA). | 2 | 900
24 | Methuen Senior Activity Center | A. Means of Egress | B. Tactile exit sign not provided | Gym | B | - | Priority 1 | Safety | Ensure that a tactile exit sign with raised characters and braille is provided at the exit door. Mount the sign between 48”- 60” above the finished floor located on the latch side of the door. Applies to the direct exit door beyond this door, and to exit door in meeting space. | 3 | 750
25 | Methuen Senior Activity Center | A. Means of Egress | B. Tactile exit sign not provided Q. Directional sign to accessible emergency exit not provided | Level 1 Corridor/East Egress,Classroom 3 Egress, Thrift Store Egresses, Auditorium Egresses | 1 | - | Priority 1 | Safety | Ensure that a tactile exit sign with raised characters and braille is provided at the exit door. Mount the sign between 48”- 60” above the finished floor located on the latch side of the door. Provide a directional sign indicating the location of the nearest accessible emergency exit. | 6 | 3000
26 | Methuen Senior Activity Center | A. Means of Egress | B. Tactile exit sign not provided P. Illuminated ISA symbol not provided (MAAB) | Main Lobby/ North/West Vestibule Entrance Applies to South/East Vestibule Entrance | 1 | - | Priority 1 | Safety | Ensure that a tactile exit sign with raised characters and braille is provided at the exit door. Mount the sign between 48”- 60” above the finished floor located on the right side of the double doors. When the illuminated sign is replaced, provide an illuminated sign with the International Symbol of Accessibility (ISA). | 2 | 500
27 | Methuen Senior Activity Center | B. Interior Access Route |  | Nurse's Office Inside Clinic | 1 | - | Priority 3 | Additional Access | Ensure the chair next to door is moved if a wheelchair user is to enter into the office. | 1 | 0
28 | Methuen Senior Activity Center | B. Interior Access Route | A. Route < 36" wide | Classroom 1 | 1 | - | Priority 3 | Additional Access | Ensure that a clear width of 36" min. is maintained at the accessible route. Relocate furniture. | 1 | 0
29 | Methuen Senior Activity Center | B. Interior Access Route | A. Route < 36" wide | Classroom 1 | 1 | - | Priority 3 | Additional Access | Ensure that a clear width of 36" min. is maintained at the accessible route. Relocate furniture. | 1 | 0
30 | Methuen Senior Activity Center | B. Interior Access Route | A. Route < 36" wide | Thrift Store | 1 | - | Priority 3 | Additional Access | Ensure that a clear width of 36" min. is maintained at the accessible route. Move shelf and trash can over. | 1 | 0
31 | Methuen Senior Activity Center | B. Interior Access Route | A. Route < 36" wide | Thrift Store | 1 | - | Priority 3 | Additional Access | Ensure that a clear width of 36" min. is maintained at the accessible route. Applies to all aisles in the thrift store. | 1 | 0
32 | Methuen Senior Activity Center | B. Interior Access Route | A. Route < 36" wide | Meeting Space | B | - | Priority 3 | Additional Access | Ensure that a clear width of 36" min. is maintained at the accessible route. Relocate furniture. | 1 | 0
33 | Methuen Senior Activity Center | B. Interior Access Route | B. Obstructed by protruding objects | Main Lobby | 1 | - | Priority 3 | Additional Access | Provide a cane-detectable barrier under the defibrillator. | 1 | 398
34 | Methuen Senior Activity Center | B. Interior Access Route | B. Obstructed by protruding objects | Auditorium/ Dining Space | 1 | - | Priority 3 | Additional Access | Provide a cane-detectable barrier on each side of the counter. Barriers must have leading edges no higher than 27” so that they are within cane sweep. Barriers can include fixed planters, benches, and guardrails. | 2 | 796
35 | Methuen Senior Activity Center | B. Interior Access Route | B. Obstructed by protruding objects | Main Lobby | 1 | - | Priority 3 | Additional Access | Provide a cane-detectable barrier on each side of the counter. Barriers must have leading edges no higher than 27” so that they are within cane sweep. Barriers can include fixed planters, benches, and guardrails. | 2 | 796
36 | Methuen Senior Activity Center | B. Interior Access Route | B. Obstructed by protruding objects | Level 1 Corridor | 1 | - | Priority 3 | Additional Access | If this shelf is not often used, recommend removing it. Otherwise provide a cane-detectable barrier. | 1 | 398
37 | Methuen Senior Activity Center | B. Interior Access Route | B. Obstructed by protruding objects | Classroom 2, Classroom 1, Classroom 3, Nurse Clinic, and Thrift Shop | 1 | - | Priority 1 | Program Access | Ensure that objects, such as signs, are located no lower than 80" above the finished floor. | 5 | 0
38 | Methuen Senior Activity Center | B. Interior Access Route | B. Obstructed by protruding objects | Classroom 2 | 1 | - | Priority 3 | Additional Access | Provide a cane-detectable barrier under the microwave. | 1 | 398
39 | Methuen Senior Activity Center | B. Interior Access Route | B. Obstructed by protruding objects | Classroom 2 | 1 | - | Priority 1 | Program Access | Provide a cane-detectable barrier at the open end of the clothes rack. | 1 | 398
40 | Methuen Senior Activity Center | B. Interior Access Route | B. Obstructed by protruding objects | Classroom 2 | 1 | - | Priority 1 | Program Access | Relocate the plant. | 1 | 0
41 | Methuen Senior Activity Center | B. Interior Access Route | B. Obstructed by protruding objects | Classroom 2 | 1 | - | Priority 3 | Additional Access | Relocate the pull string so that it is no lower than 80" above the finished floor. Applies to all ceiling fans in classrooms and corridors. | 1 | 0
42 | Methuen Senior Activity Center | B. Interior Access Route | B. Obstructed by protruding objects | Thrift Store | 1 | - | Priority 3 | Additional Access | Relocate shelf. | 1 | 0
43 | Methuen Senior Activity Center | B. Interior Access Route | B. Obstructed by protruding objects | Game Room | B | - | Priority 1 | Program Access | Relocate banners. | 1 | 0
44 | Methuen Senior Activity Center | C. Doors, Doorways, & Gates | Z. Door gets caught on surface and does not fully open | North Emergency Egress Door | B | - | Priority 3 | Additional Access | Ensure the surface is maintained in operable working condition for the door to be able to fully open. | 1 | 0
45 | Methuen Senior Activity Center | C. Doors, Doorways, & Gates | C. Maneuvering clearance(s) not provided | Women’s Multi-User Toilet Room | 1 | - | Priority 3 | Additional Access | Reverse the latch and the hinge side of the door , and relocate the paper towel dispenser so that there is 18" on the latch side of the door. (Cost is for reversing the door.) | 1 | 2449
46 | Methuen Senior Activity Center | C. Doors, Doorways, & Gates | C. Maneuvering clearance(s) not provided | Men’s Multi-User Toilet Room | 1 | - | Priority 3 | Additional Access | Move trash can and soap dispenser to provide 18" of maneuvering clearance between the edge of the door and the sink. | 1 | 0
47 | Methuen Senior Activity Center | C. Doors, Doorways, & Gates | C. Maneuvering clearance(s) not provided | Men’s Multi-User Toilet Room | 1 | - | Priority 3 | Additional Access | Remove the partition between the urinals to ensure that there is 18" clear on the latch side of the compartment door that is 60" deep. | 1 | 500
48 | Methuen Senior Activity Center | C. Doors, Doorways, & Gates | C. Maneuvering clearance(s) not provided | Classroom 2 | 1 | -- | Priority 3 | Additional Access | Remove the dolly and ensure that 18" of space on the latch side of the door is kept clear. | 1 | 0
49 | Methuen Senior Activity Center | C. Doors, Doorways, & Gates | C. Maneuvering clearance(s) not provided | Classroom 3 | 1 | - | Priority 3 | Additional Access | Ensure the programs that take place in Classroom 3 also take place in Classroom 1. Otherwise, an automatic door opener must be provided for Classroom 3. | 1 | 0
50 | Methuen Senior Activity Center | C. Doors, Doorways, & Gates | C. Maneuvering clearance(s) not provided | Thrift Store | 1 | - | Priority 3 | Additional Access | Ensure that the door is propped open during business hours. | 1 | 0
51 | Methuen Senior Activity Center | C. Doors, Doorways, & Gates | C. Maneuvering clearance(s) not provided | Game Room | B | - | Priority 3 | Additional Access | Ensure door is left open during business hours. Otherwise, an automatic door opener will be needed. | 1 | 0
52 | Methuen Senior Activity Center | C. Doors, Doorways, & Gates | C. Maneuvering clearance(s) not provided | Women's and Men's Multi-User Toilet Rooms | B | - | Priority 3 | Additional Access | Move paper towel dispenser to the toilet compartment wall on the other side of the lavatory (urinal partition wall for men's multi-user toilet room) and locate the controls no higher than 48" above the floor. Move the hand dryer above the lavatory so that it does not block the 18" maneuvering clearance on the latch side of the door, and locate the controls no higher than 48" above the floor. | 2 | 1000
53 | Methuen Senior Activity Center | C. Doors, Doorways, & Gates | E. Distance between doors in series < 48" N. Automatic door opener not operable, door does not open full 90 | Back Entrance (North Side of Building) Applies to South/East Vestibule Entrance | 1 | - | Priority 1 | Program Access | Currently the interior automatic door does not open 90 degrees, most likely due to the brick wall. We recommend relocating automatic door openers to the other set of doors in this vestibule where there is more clearance. (Cost estimate is for 2 new automatic door openers.) | 2 | 12000
54 | Methuen Senior Activity Center | C. Doors, Doorways, & Gates | G. Surface not stable, firm, and slip-resistant at entrance | Game Room | B | - | Priority 3 | Additional Access | Install new threshold. | 1 | 1000
55 | Methuen Senior Activity Center | C. Doors, Doorways, & Gates | L. Hardware not compliant | Thrift Store | 1 | - | Priority 1 | Program Access | Provide hardware that can be operable with one hand and not require tight grasping, pinching, or twisting of the wrist. | 1 | 750
56 | Methuen Senior Activity Center | C. Doors, Doorways, & Gates | L. Hardware not compliant | Gym | B | - | Priority 1 | Program Access | Provide hardware that can be operable with one hand and not require tight grasping, pinching, or twisting of the wrist. | 1 | 750
57 | Methuen Senior Activity Center | C. Doors, Doorways, & Gates | M. Door requires > 5 lbs. of force to open | Women’s and Men's Multi-User Toilet Rooms | 1 | - | Priority 3 | Additional Access | Adjust closers so doors do not require more than 5 pounds of force to open. | 2 | 0
58 | Methuen Senior Activity Center | C. Doors, Doorways, & Gates | M. Door requires > 5 lbs. of force to open | Men's and Women's Multi-User Toilet Rooms | B | - | Priority 3 | Additional Access | Adjust closers so doors do not require more than 5 pounds of force to open. | 2 | 0
59 | Methuen Senior Activity Center | D. Ramps | B. Running slope >1:12 (8.33%) | Main Lobby/ Level 1 Ramp | 1 | - | Priority 1 | Program Access | Further study will be needed to determine whether it is technically feasible to bring the ramp into full compliance with the ADA Standards. | 1 | 0
60 | Methuen Senior Activity Center | D. Ramps | B. Running slope >1:12 (8.33%) | Main Lobby/ Level 1 Ramp | 1 | - | Priority 1 | Program Access | Further study will be needed to determine whether it is technically feasible to bring the ramp into full compliance with the ADA Standards. | 1 | 0
61 | Methuen Senior Activity Center | D. Ramps | B. Running slope >1:12 (8.33%) | Main Lobby/ Level 1 Ramp | 1 | - | Priority 1 | Program Access | Further study will be needed to determine whether it is technically feasible to bring the ramp into full compliance with the ADA Standards. | 1 | 0
62 | Methuen Senior Activity Center | D. Ramps | E. Handrails do not extend 12" past top & bottom | Main Lobby/ Level 1 Ramp | 1 | - | Priority 1 | Safety | Alter handrails to extend horizontally above the landing for 12" min. beyond the top and bottom of ramp runs. | 1 | 0
63 | Methuen Senior Activity Center | D. Ramps | Q. Not maintained in operable working condition | Main Lobby/ Level 1 Ramp | 1 | - | Priority 1 | Program Access | Move basket as it is an obstruction to the lower handrail. | 1 | 0
64 | Methuen Senior Activity Center | E. Stairways | D. Handrails do not extend 12" from stairs at top E. Bottom handrail extends < 12" and one tread F. Handrails lack a compliant cross section | Main Lobby/ Main Stairwell | 1 | - | Priority 1 | Safety | Top: Ensure handrails extend horizontally above the landing for 12” min. beginning above the first riser nosing. Bottom: Ensure that the sloped bottom extension extends one tread depth min. beyond last riser nosing in same direction as stair flight. Provide handrails with 1 1/4" - 2" circular cross sections. | 1 | 0
65 | Methuen Senior Activity Center | H. LULA Elevator | B. Interior elevator door or gate is not automatic | LULA Elevator | - | - | Priority 3 | Additional Access | Ensure that the interior elevator door or gate is automatic. | 1 | 0
66 | Methuen Senior Activity Center | K. Signage | A. Signage is not provided | Main Lobby/ Leading to Auditorium | 1 |  | Priority 1 | Program Access | Locate compliant signage with raised characters and braille alongside the door on the right side of the double doors. | 1 | 250
67 | Methuen Senior Activity Center | K. Signage | A. Signage is not provided | Conference Room, Executive Director's Office | 1 | - | Priority 1 | Program Access | Locate compliant signage with raised characters and braille alongside the door on the latch side. | 2 | 500
68 | Methuen Senior Activity Center | K. Signage | A. Signage is not provided | Game Room, Gym, Ceramics Room | B | - | Priority 1 | Program Access | Locate compliant signage with raised characters and braille alongside the door on the latch side. | 3 | 750
69 | Methuen Senior Activity Center | K. Signage | B. Raised characters not provided on sign D. Braille not provided on sign G. Location of tactile sign not compliant | Classroom 1, Classroom 2, Classroom 3, Nurse Clinic, and Thrift Shop | 1 | - | Priority 2 | Navigational Issue | Provide text with raised characters duplicated in braille on the sign. Locate sign alongside the door on the latch side. | 5 | 1625
70 | Methuen Senior Activity Center | K. Signage | B. Raised characters not provided on sign D. Braille not provided on sign G. Location of tactile sign not compliant | Women’s and Men's Multi-User Toilet Rooms | 1 | - | Priority 2 | Navigational Issue | Provide text with raised characters duplicated in braille on the sign. Locate sign alongside the door on the latch side. | 2 | 500
71 | Methuen Senior Activity Center | K. Signage | B. Raised characters not provided on sign D. Braille not provided on sign G. Location of tactile sign not compliant | Men's Multi-User Toilet Room | B | - | Priority 2 | Navigational Issue | Provide text with raised characters duplicated in braille on the signs, and locate the signs alongside the door on the latch side. | 2 | 500
72 | Methuen Senior Activity Center | K. Signage | H. Non-glare finish and contrast not provided on sign | Level 1 Corridor/ Elevator | 1 |  | Priority 2 | Navigational Issue | Install a sign with a non-glare finish with characters that have a high contrast to the background. | 1 | 250
73 | Methuen Senior Activity Center | L. Service Counter | A. Counter not connected to an accessible route | Thrift Store | 1 | - | Priority 1 | Program Access | Ensure the counter is connected to an accessible route. All portions of accessible counters must be located adjacent to a walking surface. Relocated the items stored in front of the counter. | 1 | 0
74 | Methuen Senior Activity Center | M. Operable Parts / Reach Range | C. Reach < 15" or > 48"(forward/side approach) | Main Lobby | 1 | - | Priority 3 | Additional Access | Ensure that all flyers, brochures and magazines are located within reach range or ensure that staff is able to help visitors who need assistance. | 1 | 0
75 | Methuen Senior Activity Center | M. Operable Parts / Reach Range | C. Reach < 15" or > 48"(forward/side approach) | Main Lobby | 1 | - | Priority 3 | Additional Access | Provide a new table to hold the computer screen so that the highest touch screen controls are between 15"- 48" above the finished floor. | 1 | 455
76 | Methuen Senior Activity Center | M. Operable Parts / Reach Range | C. Reach < 15" or > 48"(forward/side approach) | Main Lobby | 1 | - | Priority 3 | Additional Access | Ensure that all flyers, brochures and magazines are located within reach range or ensure that staff is able to help visitors who need assistance. | 1 | 0
77 | Methuen Senior Activity Center | M. Operable Parts / Reach Range | C. Reach < 15" or > 48"(forward/side approach) | Classroom 1, Classroom 2, Changing Room in Thrift Store | 1 | - | Priority 3 | Additional Access | Provide a coat hook that is no higher than 48" above the finished floor. | 3 | 225
78 | Methuen Senior Activity Center | M. Operable Parts / Reach Range | C. Reach < 15" or > 48"(forward/side approach) | Classroom 1 | 1 | - | Priority 3 | Additional Access | Ensure that all flyers, brochures and magazines are located within reach range or ensure that staff is able to help visitors who need assistance. | 1 | 0
79 | Methuen Senior Activity Center | M. Operable Parts / Reach Range | C. Reach < 15" or > 48"(forward/side approach) | Classroom 2 | 1 | - | Priority 3 | Additional Access | Relocate paper towel dispenser so that controls are between 15"- 48" above the finished floor. | 1 | 500
80 | Methuen Senior Activity Center | M. Operable Parts / Reach Range | C. Reach < 15" or > 48"(forward/side approach) | Level 1 Corridor | 1 | - | Priority 3 | Additional Access | Ensure that staff is available to assist visitors who need assistance. | 1 | 0
81 | Methuen Senior Activity Center | M. Operable Parts / Reach Range | C. Reach < 15" or > 48"(forward/side approach) | Level 1 Corridor/Thrift Store | 1 | - | Priority 3 | Additional Access | Ensure that all flyers, brochures and magazines are located within reach range or ensure that staff is able to help visitors who need assistance. When new designation sign is installed on the latch side of the door, the pamphlet holder should be moved so it does not block 18" x 18" clear floor space for the designation sign. | 1 | 0
82 | Methuen Senior Activity Center | M. Operable Parts / Reach Range | C. Reach < 15" or > 48"(forward/side approach) | Level 1 Corridor | 1 | - | Priority 3 | Additional Access | Ensure that all flyers, brochures and magazines are located within reach range or ensure that staff is able to help visitors who need assistance. | 1
83 | Methuen Senior Activity Center | M. Operable Parts / Reach Range | C. Reach < 15" or > 48"(forward/side approach) | Level 1 Corridor | 1 | - | Priority 3 | Additional Access | Ensure that all flyers, brochures and magazines are located within reach range or ensure that staff is able to help visitors who need assistance. | 1 | 0
84 | Methuen Senior Activity Center | M. Operable Parts / Reach Range | C. Reach < 15" or > 48"(forward/side approach) | Level 1 Corridor/ Executive Director's Office | 1 | - | Priority 3 | Additional Access | Ensure that staff is available to assist visitors who need assistance with items on the lowest shelf. | 1 | 0
85 | Methuen Senior Activity Center | M. Operable Parts / Reach Range | C. Reach < 15" or > 48"(forward/side approach) | Clinic | 1 | - | Priority 3 | Additional Access | Ensure that staff is available to assist visitors who need assistance. | 1 | 0
86 | Methuen Senior Activity Center | M. Operable Parts / Reach Range | C. Reach < 15" or > 48"(forward/side approach) | Thrift Store | 1 | - | Priority 3 | Additional Access | Ensure that staff is available to assist visitors who need assistance with all products located higher than allowed. | 1 | 0
87 | Methuen Senior Activity Center | M. Operable Parts / Reach Range | C. Reach < 15" or > 48"(forward/side approach) | Basement Corridor, Game Room | B | - | Priority 3 | Additional Access | Relocate clothing rod so that controls are between 15"- 48" above the finished floor. | 2 | 150
88 | Methuen Senior Activity Center | M. Operable Parts / Reach Range | C. Reach < 15" or > 48"(forward/side approach) | Ceramics Room | B | - | Priority 3 | Additional Access | Relocate paper towel dispenser so that controls are between 15"- 48" above the finished floor and not over an obstruction. | 1 | 500
89 | Methuen Senior Activity Center | O. Dining or Work Surfaces | C. Knee or toe clearance not provided | Classroom 1 Classroom 2 | 1 | - | Priority 1 | Program Access | Provide at least one work surface with 30" min. wide knee and toe clearance. | 2 | 1400
90 | Methuen Senior Activity Center | O. Dining or Work Surfaces | C. Knee or toe clearance not provided | Ceramics Room | B | - | Priority 1 | Program Access | Provide at least one work surface with 30" min. width knee and toe clearance. | 1 | 700
91 | Methuen Senior Activity Center | O. Dining or Work Surfaces | C. Knee or toe clearance not provided G. Knee clearance less than 19" deep | Auditorium/ Dining Space | 1 | - | Priority 1 | Program Access | Provide at least one dining or work surface with 27" min. high knee and toe clearance, and with knee clearance that is 19" deep min. | 1 | 1100
92 | Methuen Senior Activity Center | O. Dining or Work Surfaces | C. Knee or toe clearance not provided G. Knee clearance less than 19" deep | Clinic | 1 | - | Priority 1 | Program Access | Provide at least one work surface with 27" min. high knee and toe clearance, and with knee clearance that is 19" deep min. | 1 | 700
93 | Methuen Senior Activity Center | O. Dining or Work Surfaces | C. Knee or toe clearance not provided G. Knee clearance less than 19" deep | Game Room | B | - | Priority 1 | Program Access | Provide at least one dining or work surface with 27" min. high knee and toe clearance, and with knee clearance that is 19" deep min. | 1 | 1100
94 | Methuen Senior Activity Center | O. Dining or Work Surfaces | C. Knee or toe clearance not provided G. Knee clearance less than 19" deep | Classroom 3 | 1 | - | Priority 1 | Program Access | Provide at least one dining or work surface with 27" min. high knee and toe clearance. For children, provide at least one dining or work surface with 24" min. high knee and toe clearance. Provide at least one dining or work surface with knee clearance that is 19" deep min. | 1 | 700
95 | Methuen Senior Activity Center | O. Dining or Work Surfaces | C. Knee or toe clearance not provided G. Knee clearance less than 19" deep | Meeting Space | B | - | Priority 1 | Program Access | Provide at least one dining or work surface with 27" min. high knee and toe clearance. Provide at least one dining or work surface with knee clearance that is 19" deep min. | 1 | 700
96 | Methuen Senior Activity Center | P. Assembly Area | P. Assistive listening devices not provided | Auditorium/ Dining Space | 1 | - | Priority 1 | Program Access | If audible communication is integral to the use of the space, provide an assistive listening system. | 1 | 5123
97 | Methuen Senior Activity Center | P. Assembly Area | P. Assistive listening devices not provided | Meeting Space | B | - | Priority 1 | Program Access | If audible communication is integral to the use of the space, provide an assistive listening system. | 1 | 1578
98 | Methuen Senior Activity Center | Q. Locker Room | J. 5% of changing rooms are not accessible | Thrift Store | 1 | - | Priority 1 | Program Access | Ensure that 5% of changing rooms (at least one) are accessible. | 1 | 7626
99 | Methuen Senior Activity Center | A. Overall Access | C. Accessible plumbing fixtures or stalls not provided | Toilet Room in Clinic | 1 | - | Priority 1 | Program Access | Provide an accessible single-user toilet room. | 1 | 31985
100 | Methuen Senior Activity Center | A. Overall Access | H. Audible alarm not provided | Women’s and Men's Multi-User Toilet Rooms | 1 | - | Priority 3 | Additional Access | When fire system is updated, ensure that an audible fire alarm is installed. | 2 | 0
101 | Methuen Senior Activity Center | A. Overall Access | H. Audible alarm not provided | Men's Multi- User Toilet Room | B | - | Priority 3 | Additional Access | When fire system is updated, ensure that an audible fire alarm is installed. | 1 | 0
102 | Methuen Senior Activity Center | B. Lavatory | B. Toe or knee clearances not provided F. Mirror above lavatory w/reflective surface > 40" | Men's Multi- User Toilet Room | 1 | - | Priority 1 | Program Access | Provide at least one lavatory with knee and toe clearance positioned for a forward approach. Lower mirror so that the bottom surface is at 40" max. above the finished floor. | 1 | 2692
103 | Methuen Senior Activity Center | B. Lavatory | B. Toe or knee clearances not provided E. Plumbing underneath is exposed F. Mirror above lavatory w/reflective surface > 40" | Women’s Multi-User Toilet Room | 1 | - | Priority 1 | Safety | Provide at least one lavatory with knee and toe clearance positioned for a forward approach. Insulate or otherwise configure pipes to prevent contact for at least one lavatory. Lower mirror so that the bottom surface is at 40" max. above the finished floor. | 1 | 2692
104 | Methuen Senior Activity Center | B. Lavatory | B. Toe or knee clearances not provided C. Lavatory rim or counter > 34" high D. Faucet is not compliant E. Plumbing underneath is exposed | Ceramics Room | B | - | Priority 1 | Safety | Provide at least one additional lavatory with knee and toe clearance positioned for a forward approach. | 1 | 2192
105 | Methuen Senior Activity Center | B. Lavatory | D. Faucet is not compliant E. Plumbing underneath is exposed F. Mirror above lavatory w/reflective surface > 40" | Men's and Women's Multi-User Toilet Rooms | B | - | Priority 1 | Safety | Provide a faucet that can be operable with one hand and not require tight grasping, pinching, or twisting of the wrist for at least one lavatory. Insulate or otherwise configure pipes to prevent contact for at least one lavatory. Lower mirror so that the bottom surface is at 40" max. above the finished floor. | 2 | 1300
106 | Methuen Senior Activity Center | D. Toilet Compartment |  | Women’s Multi-User Toilet Room | 1 | - | Priority 3 | Additional Access | Move chair so that the door can open a full 90 degrees. | 1 | 0
107 | Methuen Senior Activity Center | D. Toilet Compartment | D. Door has malfunctioning self-closing hinge | Men's and Women's Multi-User Toilet Rooms | B | - | Priority 3 | Additional Access | Repair hinge. | 2 | 0
108 | Methuen Senior Activity Center | D. Toilet Compartment | D. Door has malfunctioning self-closing hinge R. Coat hook > 48" (2010 ADA) | Women’s Multi-User Toilet Room | 1 | - | Priority 3 | Additional Access | Repair hinge. Locate the coat hook no higher than 48" above the finished floor. | 1 | 75
109 | Methuen Senior Activity Center | D. Toilet Compartment | F. Toilet seat <17" or > 19" high M. Flush control not on open side T. Centerline < or > 18" (MAAB) | Women's Multi-User Toilet Rooms | B | - | Priority 3 | Additional Access | Install a toilet with a seat height 17"- 19" above the finished floor. Provide the flush control on the open side of the toilet (transfer side). Relocate toilet so the centerline is 18" from the side wall. | 1 | 3676
110 | Methuen Senior Activity Center | D. Toilet Compartment | L. Clearance in front of the toilet < 42" clear deep (MAAB) | Women’s Multi-User Toilet Room | 1 | - | Priority 3 | Additional Access | Ensure there is a 42" min. clearance between the toilet and the nearest obstacle | 1 | 7966
111 | Methuen Senior Activity Center | D. Toilet Compartment | Q. Clearance at toilet < 72" clear depth (MAAB) | Women's Multi-User Toilet Room | B | - | Priority 3 | Additional Access | Move chair. | 1 | 0
112 | Methuen Senior Activity Center | D. Toilet Compartment | R. Coat hook > 54" (1990 ADA) | Men's Multi- User Toilet Room | 1 | - | Priority 3 | Additional Access | Locate the coat hook no higher than 48" above the finished floor. | 1 | 75
113 | Methuen Senior Activity Center | D. Toilet Compartment | F. Toilet seat <17" or > 19" high T. Centerline < or > 18" (MAAB) | Men's and Women's Multi-User Toilet Rooms | B | - | Priority 3 | Additional Access | Install a toilet with a seat height 17"- 19" above the finished floor. Relocate toilet so the centerline is 18" from the side wall. | 2 | 7352
114 | Methuen Senior Activity Center | D. Toilet Compartment | N. Noncompliant toilet paper dispenser T. Centerline < or > 18" (MAAB) V. Side grab bar < 54" from back wall | Women’s and Men's Multi-User Toilet Rooms | 1 | - | Priority 3 | Additional Access | Relocate toilet paper so that it is 24" min. high, located under the grab bar, and between 7" and 9" from the front of the toilet Relocate toilet so the centerline is 18" from the side wall. Provide a side wall grab bar that is 42" long min. located 12" max. from the rear wall. | 2 | 9952
115 | Methuen Senior Activity Center | E. Urinal | A. Rim > 17" high C. Flush control too high or not properly located | Men's Multi- User Toilet Room | 1 | - | Priority 1 | Program Access | Provide at least one urinal with the rim no higher than 17" above the finished floor. Mount flush control at 44" max. above the finished floor. | 1 | 4722
116 | Methuen Senior Activity Center | E. Urinal | A. Rim > 17" high C. Flush control too high or not properly located | Men's Multi- User Toilet Room | B | - | Priority 1 | Program Access | Provide at least one urinal with the rim no higher than 17" above the finished floor. Mount flush control at 44" max. above the finished floor. | 1 | 2611
117 | Methuen Senior Activity Center | F. Dispensers | B. Dispenser acts as a protruding object | Women’s and Men's Multi-User Toilet Rooms | 1 | - | Priority 3 | Additional Access | Relocate dispenser out of the circulation path. | 2 | 1000
118 | Methuen Senior Activity Center | A. Drinking Fountains | H. No drinking fountain provided for standing users | Gym | B | - | Priority 1 | Program Access | Provide an additional drinking fountain for standing users. | 1 | 4028
119 | Methuen Senior Activity Center | B. Sink | A. Clear floor space not provided at sink B. Toe and knee clearances not provided C. Rim or counter > 34" D. Noncompliant faucet | Gym | B | - | Priority 1 | Program Access | Provide a 30" by 48" clear floor space positioned for a forward approach. Ensure there is a 27" min. knee clearance positioned for a forward approach. Relocate sink with the front of the rim or counter no higher than 34" above the finished floor. Install faucets that do not require tight grasping, pinching, or twisting of the wrist. | 1 | 5304
120 | Methuen Senior Activity Center | B. Sink | B. Toe and knee clearances not provided C. Rim or counter > 34" | Classroom 2 | 1 | - | Priority 1 | M | Remove cabinets to ensure there is a 27" min. knee clearance positioned for a forward approach. Relocate sink with the front of the rim or counter no higher than 34" above the finished floor. | 1 | 4022
121 | Methuen Senior Activity Center | F. Exercise Machines | A. Clear floor space not provided | Gym | B | - | Priority 3 | Additional Access | Ensure that one of each type of equipment has a 30" by 48" clear floor space positioned for transfer or for use by an individual seated in a wheelchair. Clear floor space required at exercise machines and equipment shall be permitted to overlap. Applies to all unique exercise machines. | 1 | 0
122 | Methuen Senior Activity Center |  |  | Level 1 Ramp | 1 | - | Priority 4 | Enhanced Usability | Recommend providing anti-reflective covers over these signs to prevent glare. | 1 | 0
123 | Methuen Senior Activity Center |  |  | Auditorium/ Dining Space | 1 | - | Priority 4 | Enhanced Usability | Recommend providing an adjustable height podium with knee and toe clearance. | 1 | 0
124 | Methuen Senior Activity Center |  |  | Basement Corridor/ Ceramics Room | B | - | Priority 4 | Enhanced Usability | Recommend fixing lighting next to ceramics room entrance in corridor outside. | 1 | 0
125 | Methuen Senior Activity Center |  |  | Accessible Parking by Back Entrance | Ext. | - | Priority 4 | Enhanced Usability | Recommend using the term "Accessible Parking" instead of "Handicapped Parking". | 1 | 0
126 | Methuen Senior Activity Center |  |  | Entrance Door to Thrift Shop | Ext. | - | Priority 4 | Enhanced Usability | Recommend providing a solid and continuous stripe applied to the horizontal leading edge of each stair tread so that each tread is readily apparent when viewed in descent at each stair in the building. | 1 | 0